|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 23/ 01 Week 1 | X | Pre-Production Storyboard/Moodboard/Shot-List P,J,H | Pre-Production Storyboard/Moodboard/Shot-List P,J | Pre-Production Schedule P,J,H | X | X | X |
| 30/01 Week 2 | X | Pre-Production Storyboard/Moodboard/Sizzle Reel P,J,H | Pre-Production Experimentation (Studio) P,J | Pre-Production P,J,H | X | X | X |
| 6/02 Week 3 | X | Pre-Production P,J,M | Pre-Production P,J,M | Pre-Production P,J,M | X | X | X |
| 13/02 Week 4 | X | Pre-Production P,J,M | Pre-Production P,J,M | Pre-Production P,J,M | X | X | X |
| 20/02 Week 5 | X | Production P,J,M | Production P,J,M | Editing P,J,M | X | X | X |

Deadline: 26th February